**JRC Workshop: IMET modular approach and analysis - Way ahead**

|  |  |  |
| --- | --- | --- |
| **Key outcomes** | **Implemented by** | **Targeted deadline** |
| 1. IMET process – Governance
 |  |  |
| * Informal Steering Working Group on IMET (SWG-IMET)
 | JRC | July 2019 |
| 1. Communication and Visibility
 |  |  |
| * Communication strategy in view of ensuring dissemination of information and knowledge about IMET process and the BIOPAMA-IMET approach.
 | JRC and IUCN communication specialists | July 2020 |
| 1. Sustainability and Finance for assessments
 |  |  |
| * Strategy and guidelines to support the countries in being autonomous in running and owning the IMET process
 | SWG-IMET | September 2020 |
| * Communication and explanatory note on the use and the importance of IMET shall be drafted and sent to the community of donors and of users
 | Regional Observatories, JRC, DEVCO | June 2020 |
| * Establish a regional database and an ad hoc system at regional level to support national services, donors and/or other EU projects wishing to perform IMET assessments, in receiving baseline information on the process and the tool and in mobilizing coaches
 | ROs | July 2020 |
| 1. Global vs. Regional and National
 |  |  |
| **Global** |  |  |
| * Reporting and compatibility of IMET data
 | JRC BIOPAMA team based on 1st input from JRC statistical support by end of May 2020 | June 2020 |
| * Structure and common reporting format for GD-PAME
 |
| * Linkages with other PAME tools and initiatives (Green List) – SAPA – GAPA - PAGE
 | SWG-IMET, JRC IMET Support | GL: December 2020SAPA-GAPA-PAGE: June 2021 |
| * IMET-METT Converter updated to give the equivalent of the global METT value.
 | JRC: PAME Expert, Martino | October 2020 |
| **Regional** |  |  |
| * Use of IMET beyond the ACP regions
 | Voluntary process with the countries/regions which expressed interested persons in the Gran Paradiso workshop (06/20), to be encouraged by DEVCO and B4Life – Possible support from Rodrigo Tarquino and Rosa Leny Cuellar for Latin America | December 2020 |
| * Set up NON-ACP steering group, concept note to promote the use of IMET in NON-ACP countries and to adopt a coordinated approach with DEVCO and to ensure coordination with the SWG-IMET
 | Interested NON-ACP countries and SWG-IMET | November 2020 |
| 1. IMET Next steps
 |  |  |
| * IMET 2.0 last release: finalised and accessible to everybody
 | JRC | June 2020 |
| * Customise and finalise the integration of key marine elements within IMET 2.0, based on a joint work JRC, KWS and other key marine experts
 | JRC, KWS, MPAs experts, … | Agreed content by September 2020 agreed content, IT development / release by March 2021 |
| * Development of an excel version of the IMET modules on Law Enforcement and on Governance of Ecosystem services – Field test phase and revisions – Development of the IT versions
 | OFAC, ESARO, JRC,RAMPAO  | Excel: October 2019Field tests and revisions: November 2020IT version: May 2021 |
| * Planning-Monitoring-Evaluation module shall be structurally associated with IMET and its modules
 | JRC, based on outcomes of tests on the modules | February 2021 |
| * Development of the cross-analysis as supporting tool for site analysis and many other aspects (thematic, scaling up, etc.)
 | JRC and statistical support, JRC-IT | Concept note and identification of priority developments by November 2020;IT correlated developments and applications by April 2021 |
| * Test IMET 2.0 (as it is) in CBAs and see how it works and how it is perceived, then involve CBAs specialists in a reflection on possible adaptation of IMET 2.0 to a lighter module responding to CBAs’ needs for management effectiveness evaluation
 | Madagascar via Domoina and Pacific Regional Observatory? | Madagascar and Pacific: reflection and identification of pilot test site by November 2020; tests implemented by June 2021 |
| * Coordination with IUCN-Green List (GL) to share experiences, to identify and operationalise) synergy and to jointly agree on possible cross-walks between IMET 2.0 and GL
 | IUCN-GL and JRC | September 2020 |
| * Focus on ad hoc visualisation and reports for the PA level and on a ‘tableau de bord’ approach to the country level
 | Coaches, OFAC, JRC, IUCN)  | January 2021 |
| 1. Capacity building
 |  |  |
| Drafting of a capacity-building strategy | IUCN in coordination with JRC | by July 2020 |
| **General recommendations on the Coaches and the Coaching process** |  |  |
| * Criteria and process for selection and ‘certification’ of coaches so as to ensure efficiency and uptake
 | Coaches, OFAC, ESARO, IUCN, JRC | November 2020 |
| * Relationship between coaches/BIOPAMA – training, funds, contract conditions, further certification based on experience, etc. –
 | Coaches, IUCN, JRC | by March 2021 |
| * Organize a training course for coaches in English and then in Spanish
 | IUCN + JRC, DEVCO, Peru’, Bolivia | February 2020 (EN)April 2021 (ESP) |
| * Support, training, collaboration and coordination with GL mentors
 | IUCN-GL, JRC | by April 2021 |
| **IMET and analysis – COMIT – strengthening of regional and national levels** |  |  |
| * New and updated version of COMIT produced by IUCN PACO – IMET 2.0 and guidelines for analysis at site level and at system level
* short version of the COMIT
 | IUCN | * by July 2020
 |
| **Capacity Building on the new modules – after tests and development –** |  |  |
| * Capacity building and coaching on the new IMET modules once tested and approved
 | IUCN, JRC, Coaches, ROs | by end of 2020 |
| **Widen the scope of IMET training beyond PAs practitioners** |  |  |
| * Expand training offer beyond national agencies and to stakeholders
 | BIOPAMA, JRC | by end of 2020 |
| **IMET Community and communities of practice**  |  |  |
| * Setting up a community of practice to coordinate the work and to pro-actively communicate with the IMET community
 | (IUCN, JRC, Coaches, SWG-IMET) | active set-up of community of practice by September 2020 |
| **IMET training modules** |  |  |
| * List of the different IMET-related training available so far or to be developed
 | IUCN, JRC, ROs | July 2020 |
| 1. Analysis and Decision Support Systems
 |  |  |
| * Active involvement of an institution directly engaged in the political and the technical debate with the National Agencies, such as RAPAC
 | MSs, COMIFAC, UEMOA | March 2021 |
| **Processing vs. Analysis – 2 different profiles –** |  |  |
| * Ownership on processing and analysis – statistics and analysis – by Regional Observatories and national services.
 | ROs, JRC, IUCN | From April 2021 |
| **Customisation of IMET forms to respond to specific mandatory national needs** | To develop |  |
| * Customise IMET to address specific needs possible but:
 |  |  |
| * + drafting specific guidelines for API-IMET related IMET development
 | JRC | by end of 2020 |
| * + ensure the integration of the IMET database into the RRIS (and into national services websites if requested, with the support of ROs)
 | JRC, ROs | from end of 2020 |
| **Monitoring-Planning-Evaluation approach** |  |  |
| * Dedicated approach and training strategy and material in promoting the Planning, Monitoring and Evaluation – PME – approach
 | JRC+IUCN | October 2020 |
| **How best pro-actively supporting decision support systems – DSS –** |  |  |
| * Development of specific visualisation products – DSS – and training to the decision-makers community at different levels
 | ROs | by May 2021 |
| **Statistics and cross-analysis** |  |  |
| * Developments of the cross-analysis approach and related applications (including engaging with the user community) to support quality and reliability of field assessments
 | JRC, SWG-IMET | by May 2021 |
| * Capacity building in cross analysis
 | IUCN, JRC | From May 2021 |
| 1. Regional Observatories and Data management
 |  |  |
| **Data access, data sharing, data property and visualisation** |  |  |
| * Guidelines for specific data sharing and data property between the countries and the Regional Observatories
 | JRC, ROs | by January 2021 |
| * ROs and national agencies to clarify data sharing and data visualisation issues, modalities and limitations, etc.
 | OFAC, RAMPAO, WARO, RCMRD (ESARO) | by November 2020 |
| **Database access and structure – including statistics –** |  |  |
| * Integrate/associate the statistical programs used to process IMET data for scaling-up purposes to the database package
 | JRC | December 2020 |
| * Support the regional and the national levels through capacity-building and training processes
 | JRC, IUCN | by March 2021 |
| **Governance of data** |  |  |
| * Identify key stakeholders and their roles and access rights – decision maker and data collector, user, managers – to data
 | ROs | by October 2020 |
| **Role of the Regional Observatories & link with National Agencies** |  |  |
| * More transparency and relationship between ROs – National services – IUCN – JRC
 | IUCN, JRC | by November 20120 |
| **Follow-up of ME assessments** |  |  |
| * Development in the RIS – /RRIS – a monitoring system to follow-up the level of implementation of the recommendations from PAME assessments tool in view of supporting PAs and National services
 | JRC, IUCN, ROs | by December 2020 |
| **Linkages between RIS and IMET** |  |  |
| * Promote structural and functional link between IMET database and the RIS/RRIS
 | JRC IT Team | By October 2020 |
| **Integration of DOPA & Copernicus in the work of the ROs** |  |  |
| * Ensure integration and full accessibility of data/services of DOPA – Copernicus – BIOPAMA into the RIS/RRIS
 | JRC, ROs | By June 2021 |
| * Ensure the download of all relevant information from DOPA and Copernicus to support pre-filling or IMET analysis
 | JRC | by May 2020 |